Submission Date: 2026 March 30

Requested By: Hapag-Lloyd

Submitted By: Avathon

1.	Background: A Strategic Partner for Hapag-Lloyd	2

1.1	Technological Readiness & Future Proofing	2

1.3 Leadership Team Driving Operational Rigor	3

2.	Problem Definition of Use Cases	4

2.1 Upstream Use Cases (Pilot: Weeks 0–6)	4

2.2 Additional Use Cases (Phase 2)	5

2.3 KPI for Pilot and Enterprise Agreement	5

3.	Strategic Approach and Phased Delivery Acceleration	6

4.	Program Schedule for Delivery	7

5.	Risk Assessment & Mitigation Strategies	7

6. Rough Order of Magnitude	8

7. Terms & Conditions	9

8. Acceptance & Signatures	9

# Background: A Strategic Partner for Hapag-Lloyd

Avathon is a full-spectrum AI company operating across capital-intensive sectors, with demonstrated operational depth and commercial focus in Logistics and Transportation. We specialize in transforming complex, fragmented data into actionable intelligence.

For Hapag-Lloyd, one of the world's leading ocean container shipping companies, Avathon proposes to apply its AI expertise to the freight audit challenge: systematically eliminating the invoice errors and contract mismatches that drive freight disputes, customer service burden, and regulatory exposure.

## Technological Readiness & Future Proofing

We are designed to handle multiple data output formats, including XML/SGML, JSON, PDF, CSV, TXT with additional data connectors for static and real-time data ingestion. Avathon is structured to begin immediately on static data (PDF, CSVs) without requiring deep system integration, enabling a 6-week proof of concept that demonstrates measurable value before enterprise commitment.

Avathon specializes in extracting structured data from complex, heterogeneous documents such as contracts, tariff tables, rate cards, and bid packages. This is exactly the document ecosystem at the center of Hapag-Lloyd's dispute challenge, where Avathon can deliver Natural Language Processing (NLP) at Scale.

At the center of our future-proofed solution is the Computational Knowledge Graph (CKG) - a modern architectural backbone that replaces modeling and rigid data structures with a fully data unified, semantically rich model.

The platform uses commercial off-the-shelf identity services and configurable, secure Role-Based Access Control (RBAC), all deployed on a high-performance Data Lakehouse that immediately scales up to and customer requirements. Further this architecture supports true semantic modeling, where data engineers can define and extend data relationships through JavaScript and Python workflows. This technology differentiator is a key workbench enabler for planners, sales, and service teams.

To address key feature development and a final key differentiator, the platform is structurally capable to support AI workflows and Agentic Compute. Every recommendation can include full data auditability enabling users to verify data points and ensuring customers can trust the system’s outputs (a key weakness of current data normalization processes).

## 1.3 Leadership Team Driving Operational Rigor

Our teams bring a wealth of operational experience directly to this engagement. Across the c-suite and management team there is a wealth of knowledge in supply chain and logistics.

- Executive Leadership: Led by CEO Pervinder Johar, brings three decades of expertise in AI, ML, SaaS, and supply chain. Former CEO of Blume Global (WiseTech), with senior roles at Hewlett Packard, Manhattan Associates, and EdgeVerve. Chair of the Board of Advisors at 25m Supply Chain and Forbes Technology Council member.

- Engineering Leadership: Led by SVP Santosh Pant, emphasizes stability, scalability (via AKS), and adherence to the rigid standards. Having deployed multiple logistics and transportation solutions and served as SVP of R&D at Blume Global and Rez-with a proven track record in architecting fleet management and planning capabilities

- Commercial Leadership: Led by CCO David Arsenault, brings 25 years with global ocean carriers including former President & CEO of Hyundai Merchant Marine America. Senior roles at Sea-Land, Maersk, GT Nexus, and DCLI. Graduate of the U.S. Merchant Marine Academy and Board member of the Propeller Club of LA and Long Beach.

# Problem Definition of Use Cases

Every freight dispute Hapag-Lloyd handles today was caused by an error that might have existed before the customer ever filed a dispute. These opportunities for errors occurred when a contract was built, a rate was keyed, or a bid package was translated into FIS. Avathon's upstream use cases target those exact moments: the daily decisions made by pricing planners, sales teams, and contract administrators as they negotiate, codify, and enter customer agreements. By catching discrepancies at the source, Hapag-Lloyd teams can resolve them in seconds during contract setup rather than spending 20 minutes per dispute after the invoice has already been issued.

## 2.1 Upstream Use Cases (Pilot: Weeks 0–6)

The following three use cases represent the highest-value, immediately actionable opportunities within the pilot. Each is scoped to work on static data (PDFs and Excel exports) without requiring live system integration.

Use Case 1: Contract Review

When a pricing planner or sales rep finalizes a service contract with a shipper, that contract often arrives as a customer-dictated contract with non-standard language around free time, calendar vs. working day definitions, tier structures, and accessorial rules. Today there is no systematic check to Hapag's boilerplates on those terms. Avathon will use NLP to extract, map, and read both the customer contract and Hapag's standard boilerplate to flag clause that deviates.

- Who uses it: Pricing planners and sales directors during contract negotiation and onboarding.

- When it occurs: At contract execution; before rates are entered into any system.

- What it catches: Ambiguous free-time language (calendar vs. working days), non-standard tier logic, missing accessorial definitions, and terms that conflict with Hapag's standard boilerplate.

- Output: A clause-by-clause comparison report flagging deviations above the Hapag standard baseline, with confidence scores and plain-language descriptions of each anomaly.

Use Case 2: Rate Entry Verification

After a contract is signed, rates and terms from bid files (GT Nexus, Excel) must be manually transcribed into FIS. This is where fat-finger errors, rounding mistakes, and field-mapping failures are introduced. A pricing planner has no automated way to confirm that what is in FIS reflects what the contract says. Avathon compares the FIS rate extract against the executed contract and the original bid package, and flags any line that doesn't match, before an invoice is ever generated.

- Who uses it: Pricing planners and rate desk administrators after contract execution, during FIS data entry.

- When it occurs: After rates are entered into FIS; before any shipment is rated or invoiced.

- What it catches: Rate mismatches between bid package and FIS entry, incorrect surcharge codes, missing accessorial charges, and rounding/truncation errors.

- Output: A field-level validation report showing FIS entry rates against the source contract value, with a pass/flag/fail status and the specific discrepancy identified.

## 2.2 Additional Use Cases (Phase 2)

The following use cases become unlocked once the pilot has validated the core AI pipeline and Hapag-Lloyd has confirmed the level of system integration that is feasible. Each represents a further step upstream in the process where errors can be eliminated before they reach the customer.

- Rate Card Alignment & 3rd Party Reconciliation (Sales): When a sales rep or CS rep is responding to a customer rate query or confirming a booking via GT Nexus or another 3rd party platform, Avathon automatically compares the customer-facing rate against the Hapag FIS-coded rate and flags any discrepancy before it reaches the customer as a disputed invoice.

- Pre-Booking Rate Confirmation (Sales): Before a sales rep accepts an export booking, Avathon validates the applied rate against the customer's active service contract. If the rate doesn't match, the rep sees a flag before the booking is confirmed; not after the cargo has sailed.

- Invoice Pre-Audit Gate (CS / Billing): Before any invoice is released to a customer, Avathon applies a confidence score based on the validated contract and rate data. Low-confidence invoices are routed to a CS reviewer queue for correction. High-confidence invoices are released automatically.

- D&D Free-Time Validation (CS / Operations): Before D&D terms are transmitted to PayCargo, Avathon validates the contracted free-time allowances against the executed service contract. The CS rep or planner sees a confirmation that what PayCargo will use to compute elapsed days is exactly what the customer signed.

- Shipping Instructions & BOL Validation (Documentation): Within 3 days of vessel sailing, Avathon ingests Shipping Instructions for U.S. imports and validates Bill of Lading terms against the service contract, flagging discrepancies for the documentation team before the BOL is issued.

## 2.3 KPI for Pilot and Enterprise Agreement

The first and primary KPI for success is Invoice Dispute Rate. This represents Avathon and Hapag-Lloyd's shared north-star goal of driving freight penalty disputes to zero. Baseline values are drawn from the March 19, 2026 discovery workshop. All KPIs will be formally agreed upon and baselined by Week 1 of the pilot.

| KPI | Baseline | Pilot Target | Enterprise Target |
| --- | --- | --- | --- |
| Invoice Dispute Rate | ~9% of invoices | <5% | <1% (toward zero) |

# Strategic Approach and Phased Delivery Acceleration

This Statement of Work governs a 6-week pilot engagement primarily for the upstream problem areas (contract extraction and rate card comparison) structured as follows: 3–4 weeks of pipeline build and model development using static data, followed by 2 weeks of validation, refinement, and readout. The pilot is scoped to static data dumps only; deep system integration (FIS, PayCargo, GT Nexus live APIs) is deferred to Phase 2. Time and Materials will include 2 FTE engineers and 1 FTE senior manager.

| # | Deliverable | Description | Output |
| --- | --- | --- | --- |
| D1 | Technical Session plus Data Ingestion & Pipeline Setup | Map end-to-end flow of where errors are introduced (bid → contract → FIS entry → invoice), plus agreed data fields to extract (rates, accessorials, free time, calendar/working day rules, tier logic, exceptions, tariff references) Ingest static data dumps (PDF, Excel, CSV): customer contracts, rate cards (Hapag FIS extract, GT Nexus/3rd-party bid packages), and dispute history samples. Establish bronze/silver/gold data pipeline architecture. | Structured data lake with raw → enriched → scored layers; data inventory report |
| D2 | Contract Term Extraction & Mapping (NLP) | Apply NLP models to extract key contract clauses from customer boilerplate and Hapag standard contract templates. | Extracted clause library; boilerplate vs. customer-specific anomaly flags; confidence scoring per clause |
| D3 | Rate Card Comparison Mapping | Automate rate-card-to-rate-card comparison between Hapag-coded rates (FIS) and 3rd-party bid packages (GT Nexus, Excel). Flag potential discrepancies before invoicing. Identify fat-finger, rounding, and field-mapping errors. | Mismatch flag report with evidence (source clause/rate); yes/no review queue with dispute type classification |
| D4 | SME Validation & Rules Refinement | Hapag-Lloyd SMEs review AI outputs against a representative sample of real dispute cases. Measure true positive / false positive rates on rate-card mismatches and contract term extraction. Iteratively refine extraction rules and confidence thresholds for calendar vs. working day defaults, tier-rate logic, and free-time resets. | Annotated validation set; precision/recall report; updated prompt and rules library; agreed confidence threshold for production use |
| D5 | Pilot UI & Phase 2 Roadmap | Present pilot results in an UI against agreed KPIs. Define Phase 2 roadmap covering full invoice pre-audit gate, FIS input validation, D&D/PayCargo pre-audit, pre-booking rate confirmation, and customer inquiry automation. Deliver commercial model and integration approach proposal. | Pilot outcomes report; Phase 2 SOW draft; commercial and integration model; MSA execution ready |

# Program Schedule for Delivery

The pilot is structured across 6 weeks with the following milestone schedule:

- Week 1 (Kickoff & Data Intake): SOW executed; pilot data package delivered by Hapag-Lloyd (boilerplate contracts, rate cards, dispute history samples); security and GDPR data-sharing path confirmed; technical whiteboard session conducted and end-to-end error flow mapped (bid → contract → FIS → invoice).

- Week 1–2 (Reference Materials): Hapag-Lloyd to provide briefcase/checklist template, internal coding glossary, free-time definitions, and charge code acceptance constraints by key customer.

- Weeks 2–3 (Pipeline Build): Avathon builds bronze/silver/gold data pipeline. Ingests static contract and rate card data. Delivers initial contract term extraction library and semantic clause clustering.

- Weeks 3–4 (Rate Card Engine): Rate-card-to-rate-card comparison engine built and run against pilot data set. Mismatch flags generated with source evidence and dispute type classification. Initial confidence scoring applied.

- Weeks 4–5 (SME Validation): Hapag-Lloyd SMEs review AI outputs against real dispute samples. True positive / false positive rates measured. Extraction rules and confidence thresholds refined iteratively.

- Week 6 (Pilot Readout): Results presented against agreed KPIs. Phase 2 roadmap defined with a MSA and commercial model proposed.

# Risk Assessment & Mitigation Strategies

To enable successful delivery, completion of the proposed solution and mitigate risk across the project timeline, Avathon has identified risk mitigation strategies.

| Risk Category | Risk | Mitigation Strategy |
| --- | --- | --- |
| Data Quality & Completeness | Incomplete or inconsistently formatted contract PDFs and rate card data may reduce NLP extraction accuracy and delay pipeline build. | Front-load a data inventory review in Week 0–1. Hapag-Lloyd to provide minimum 2 years of representative samples. Define minimum data quality thresholds before pilot launch. |
| Integration Complexity | Deep system integration (FIS, PayCargo, GT Nexus) carries scope risk. Early phase reliance on static data dumps may not fully reflect live data conditions. | Pilot scoped to static data only. Integration design documented but deferred to Phase 2. Scope change board established to govern additions. |
| Ambiguous Contract Language | Non-standard customer boilerplates (major shipper dictated terms), calendar vs. working day ambiguities, and tariff interaction rules may generate false positives. | Hapag SME validation sessions in Weeks 2–4. Briefcase/checklist and internal code library provided by Hapag-Lloyd in Week 0–2. Iterative prompt and rules refinement cycle built into pilot. |
| Stakeholder Alignment | Multiple Hapag-Lloyd business units involved (Customer Service, Sales, Process Excellence, IT). Misaligned priorities may slow decision-making. | Joint Steering Committee established with an executive sponsor. Weekly syncs with defined RACI. Clear pilot SOW criteria agreed upfront. |

# 6. Rough Order of Magnitude

Avathon is pleased to submit this ROM, based on Hapag’s SSOW requirements and insights from the March workshop.

| Component | Pilot (Weeks 0–6) | Enterprise Phase 2+ |
| --- | --- | --- |
| Agreement Term | 6 Weeks (Pilot) | 12-Month Subscription (TBD) |
| Engagement Model | Time & Materials | Enterprise Subscription + SLA |
| Resource Commitment | 2 Forward Engineers + Senior Lead | Dedicated pod (TBD in Phase 2 SOW) |
| Estimated Pilot Cost | $165,000 | — |

Avathon will provide forward engineer T&M rates and a detailed cost breakdown upon scope confirmation and Hapag-Lloyd's acceptance of this SOW.

# 7. Terms & Conditions

- This SOW is governed by the existing Non-Disclosure Agreement (NDA) between Avathon and Hapag-Lloyd.

- All customer contract data shared during the pilot will be handled per agreed data redaction/protection guidelines confirmed by both parties' legal and security teams.

- This pilot engagement is Time & Materials. Neither party is obligated to proceed to Phase 2 / enterprise subscription without execution of a separate Master Services Agreement (MSA).

- Scope changes during the pilot must be approved by both parties' designated project leads and documented in a written change order.

- Severity levels for issue escalation during the pilot: Severity 1 (Critical): System non-availability; Severity 2 (High): Severe impairment causing delay; Severity 3 (Medium): Functional impairment causing inconvenience; Severity 4 (Low): Single-user impact.

# 8. Acceptance & Signatures

By signing below, both parties agree to the scope, deliverables, KPIs, schedule, and responsibilities defined in this Statement of Work.

| AVATHON, INC. | HAPAG-LLOYD AG |
| --- | --- |
| Authorized Signature: ___________________________ | Authorized Signature: ___________________________ |
| Printed Name: ___________________________ | Printed Name: ___________________________ |
| Title: ___________________________ | Title: ___________________________ |
| Date: ___________________________ | Date: ___________________________ |